## Project Overview
Project | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | Legend
Webhannet
Engineering
Bragdon/Charles Bridge | bar: 2021-04-01
Staff and Stakeholder Review
Pine Ledge/Robinson/Ridgetop
State/Federal Permits
Drakes Island bridge
Public Engagement
Swamp John Rd
Bid Process
Casino Square
On-site work
Dike St drainage | [18 empty] | Complete
Newhall Rd

## Webhannet Sea Walls
Project | Stakeholders | Communication Expectation | Timeline | Stakeholder Action Plan
Webhannet North and South/FEMA Repair | Residents of Webhannet RD | Inform and Consult | By June 1 2021 | Neighborhood meeting and email sign up for updates
| Select Board | Inform and Consult | Monthly Update | Updates monthly
Funding Source | Fire | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
Bond/FEMA Reimburse | Planning | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
| Police | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
Engineering Status | Dubois King | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
Not yet started | School Department | Inform
| WEMS | Inform
| MEMA Representative | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
| MDEP | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
| Army Corp? | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
| KK&W | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
| Wells Sanitary District | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
| Spectrum | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
| Phone | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
| CMP | Collaborate | Fall and Winter 2020/2021 | Initial project kick-off meeting, meetings to plan as needed
FY21 Paving Plan

## Bragdon Rd Culvert and Bridge
Project | Stakeholders | Communication Expectation | Timeline | Stakeholder Action Plan
Bragdon Rd Culvert/Charles Something Bridge | Bragdon Rd Residents | Inform and Consult | Public Information Meeting March 2021
| Town Residents | Inform and Consult | Public Information Meeting March 2021
Funding Source | Select Board | Inform and Consult | Monthly Update
Emergency Infrastructure Fund | Planning | Collaborate | Meeting with DK mid-November 2020
| Fire | Collaborate | Meeting with DK mid-November 2020
Engineering Status | Police | Collaborate | Meeting with DK mid-November 2020
Not yet started | School Department | Inform
| WEMS | Inform
| Dubois King | Collaborate | Design work complete by December 31
| MDEP | Collaborate | Permit by February 28, 2021
| Phone | Collaborate | Inform fall 2020, Meet with DK January 2021
| CMP | Collaborate | Inform fall 2020, Meet with DK January 2021
| Spectrum | Collaborate | Inform fall 2020, Meet with DK January 2021

## Pine LedgeRobinsonRidgetop
Project | Stakeholders | Communication Expectation | Timeline | Stakeholder Action Plan
Pine Ledge/Robinson/Ridgetop | Residents of all Three Roads | Inform and Consult | January, 2021 | Neighborhood meeting, monthly email communications for those that sign up
| Select Board | Inform and Consult | Monthly | Board meeting updates
Funding Source | Planning | Inform
Bond | Fire | Inform
| Police | Inform
Engineering Status | CMA Engineers | Collaborate | Complete February
In process | KK&W | Collaborate | Ongoing | Include KK&W work in bid process
| MDEP | Collaborate | Complete February | Site specific permit

## Drakes Island Bridge
Project | Stakeholders | Communication Expectation | Timeline | Stakeholder Action Plan
Drakes Island Bridge | Drakes Island Association | Inform and Consult | June 2021 meeting | Neighborhood meeting and email updates for those that sign up
| Select Board | Inform and Consult |  | Monthly update
Funding Source | Planning | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
Bond | Police | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
| Fire | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
Engineering Status | Dubois and King | Collaborate | Begin in October 2020 | Engineering meetings with DPW, staff and stakeholder review meetings
Not yet started | School Department | Inform |  | Updates as needed
| Rachel Carson | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
| Audubon | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
| MDEP | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
| IF&W | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
| Laudholm Farm | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
| KK&W | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
| Wells Sanitary District | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
| Phone | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
| Spectrum | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings
| CMP | Collaborate | Begin in October 2020 | Staff and stakeholder review meetings

## Swamp John Rd
Project | Stakeholders | Communication Expectation | Timeline | Stakeholder Action Plan
Swamp John Rd | Residents/Local businesses | Inform and consult | 2021-01-01 | Neighborhhod meeting and monthly email updates for those that sign up
| DEP | Inform and consult | Monthly | Meeting updates
Funding Source | Public Safety | Collaborate | 2021-03-01 | Staff review meeting
Bond | CMA Engineers | Collaborate | Monthly through bid | Meetings as needed
| MDEP | Collaborate | Complete February 2021 | Permit application
Engineering Status
In final design

## Casino Square Sea Wall
Project | Stakeholders | Communication Expectation | Timeline | Stakeholder Action Plan
Casino Square Sea Wall Design | Residents and Business Community | Inform and consult | May, July, and September 2021 | Neighborhood/businesses meeting
| Select Board | Inform and consult | monthly | Meeting updates
Funding Source | Public Safety | Collaborate | May - August 2021 | Development meetings
Bond and Economic Development grant | Dubois and King | Collaborate | May - August 2022
| MDEP | Collaborate | begin winter 2021 | Permitting process
Engineering Status | Army Corps | Collaborate
Not yet started | Audubon | Collaborate
| KK&W | Collaborate | As needed | Development meetings
| Wells Sanitary | Collaborate | As needed
| Federal Economic Development Grant | Collaborate | As needed
| Phone | Collaborate | As needed
| Spectrum | Collaborate | As needed
| CMP | Collaborate | As needed

## Dike St Drainage
Project | Stakeholders | Communication Expectation | Timeline | Stakeholder Action Plan
Dike St Drainage
Funding Source
Engineering Status

## Newhall Rd
Project | Stakeholders | Communication Expectation | Timeline | Stakeholder Action Plan
Newhall Rd
Funding Source
Emergency Infrastructure
Engineering Status

## FY22 Paving Plan
Road | Estimated Cost | Stakeholders | Communication Expectation | Timeline | Stakeholder Action Plan